## Sheet1
CEI WEEKLY SUMMARY OF EVENTS, OBSERVATIONS AND REMARKS
Prepared for: |  | Jackson County, FL
Prepared by: |  | Alday-Howell Engineering, Inc.
Prepared on: |  | 2025-09-28
For Project: |  | Indian Springs Sewer Phase 2D
|  | NWFWMD Const. Grant Agreement No. 20-036 |  |  |  |  | AHE # 23-012
Contractor: |  | Blankenship Contracting, Inc.
Designer: |  | Alday-Howell, Engineering |  |  |  | Inspector: | Dwayne Josey 850-258-3386
Notice to Proceed: |  | 2024-11-04 |  |  | Award Date: | 2022-12-13
|  | Substantial Completion: | 2026-08-03 |  |  |  |  | Final Completion: | 2026-10-02
The report is for the week of: |  |  | Monday, | 2025-09-22 |  |  | thru Sunday, |  | 2025-09-28
The contractor performed the following operations this week. Sub work is noted in parenthesis:
Monday- |  | No work. Contractor's option.
Tuesday- |  | No work. Contractor's option.
Wednesday- |  | No work. Contractor's option.
Thursday- |  | No work. Contractor's option.
Friday- |  | No work at contractor's option.
Saturday- |  | No work at contractor's option.
Sunday- |  | No work at contractor's option.
Engineer's remarks/Pending issues: |  |  |  | Percent complete is phase specific, invoiced is per project.
Percent Project Complete: |  |  | 0% |  |  |  | Time Remaining (%): |  | 51.33%
Invoiced to Date: |  |  | 1085658.93 |  |  |  | Weather days to date: |  | 16
Original Contract Amount: |  |  | 6377639.99
Change Order Amount Approved: |  |  | 2820626.04 |  |  |  | Holiday days granted: |  | 21
Contract Time Approved: |  |  | 300 |  |  |  | Actual Days: |  | 329
Remaining: |  |  | 8112607.1 |  |  |  | Days used with deduct: |  | 292
Days to Substantial Completion: |  |  | 600 | Original SC: 300 |  |  | Remaining to SC: |  | 308
Days to Final Completion: |  |  | 660 | Original FC: 360 |  |  | Remaining to FC: |  | 368
Approved: | Robin G. Besczezynski, Utility Project Manager (850-526-2040)

## Chart Data
DATE | % Complete | % Payment | Rain Day | Holiday | No work
2022-09-27 | 1% |  |  |  | 1%
2022-09-28 |  |  |  |  | 100%
2022-09-29
2022-09-30 |  |  |  |  | 100%
2022-10-01
2022-10-02 | 2%
2022-10-03 |  |  | 100%
2022-10-04
2022-10-05 |  |  |  | 100%
2022-10-06 |  |  |  |  | 100%
2022-10-07
2022-10-08
2022-10-09
2022-10-10
2022-10-11 | 5%
2022-10-12
2022-10-13
2022-10-14
2022-10-15
2022-10-16
2022-10-17
2022-10-18
2022-10-19
2022-10-20
2022-10-21
2022-10-22
2022-10-23
2022-10-24
2022-10-25 | 10%
2022-10-26
2022-10-27
2022-10-28
2022-10-29
2022-10-30
2022-10-31
2022-11-01 | 22%
2022-11-02
2022-11-03
2022-11-04
2022-11-05
2022-11-06
2022-11-07
2022-11-08 | 25%
2022-11-09
2022-11-10
2022-11-11
2022-11-12
2022-11-13
2022-11-14
2022-11-15
2022-11-16
2022-11-17
2022-11-18
2022-11-19
2022-11-20
2022-11-21
2022-11-22
2022-11-23
2022-11-24
2022-11-25
2022-11-26
2022-11-27
2022-11-28
2022-11-29
2022-11-30
2022-12-01
2022-12-02
2022-12-03
2022-12-04
2022-12-05
2022-12-06
2022-12-07
2022-12-08
2022-12-09
2022-12-10
2022-12-11
2022-12-12
2022-12-13
2022-12-14
2022-12-15
2022-12-16
2022-12-17
2022-12-18
2022-12-19
2022-12-20
2022-12-21
2022-12-22
2022-12-23
2022-12-24
2022-12-25
2022-12-26
2022-12-27
2022-12-28
2022-12-29
2022-12-30
2022-12-31
2023-01-01
2023-01-02
2023-01-03
2023-01-04
2023-01-05
2023-01-06
2023-01-07
2023-01-08
2023-01-09
2023-01-10
2023-01-11
2023-01-12
2023-01-13
2023-01-14
2023-01-15
2023-01-16
2023-01-17
2023-01-18
2023-01-19
2023-01-20
2023-01-21
2023-01-22
2023-01-23
2023-01-24
2023-01-25
2023-01-26
2023-01-27
2023-01-28
2023-01-29
2023-01-30
2023-01-31
2023-02-01
2023-02-02
2023-02-03
2023-02-04
2023-02-05
2023-02-06
2023-02-07
2023-02-08
2023-02-09
2023-02-10
2023-02-11
2023-02-12
2023-02-13
2023-02-14
2023-02-15
2023-02-16
2023-02-17
2023-02-18
2023-02-19
2023-02-20
2023-02-21
2023-02-22
2023-02-23
2023-02-24
2023-02-25
2023-02-26
2023-02-27
2023-02-28
2023-03-01
2023-03-02
2023-03-03
2023-03-04
2023-03-05
2023-03-06
2023-03-07
2023-03-08
2023-03-09
2023-03-10
2023-03-11
2023-03-12
2023-03-13
2023-03-14
2023-03-15
2023-03-16
2023-03-17
2023-03-18
2023-03-19
2023-03-20
2023-03-21
2023-03-22
2023-03-23
2023-03-24
2023-03-25
2023-03-26
2023-03-27
2023-03-28
2023-03-29
2023-03-30
2023-03-31
2023-04-01
2023-04-02
2023-04-03
2023-04-04
2023-04-05
2023-04-06
2023-04-07
2023-04-08
2023-04-09
2023-04-10
2023-04-11
2023-04-12
2023-04-13
2023-04-14
2023-04-15
2023-04-16
2023-04-17
2023-04-18
2023-04-19
2023-04-20
2023-04-21
2023-04-22
2023-04-23
2023-04-24
2023-04-25
2023-04-26
2023-04-27
2023-04-28
2023-04-29
2023-04-30
2023-05-01
2023-05-02
2023-05-03
2023-05-04
2023-05-05
2023-05-06
2023-05-07
2023-05-08
2023-05-09
2023-05-10
2023-05-11
2023-05-12
2023-05-13
2023-05-14
2023-05-15
2023-05-16
2023-05-17
2023-05-18
2023-05-19
2023-05-20
2023-05-21
2023-05-22
2023-05-23
2023-05-24
2023-05-25
2023-05-26
2023-05-27
2023-05-28
2023-05-29
2023-05-30
2023-05-31
2023-06-01
2023-06-02
2023-06-03
2023-06-04
2023-06-05
2023-06-06
2023-06-07
2023-06-08
2023-06-09
2023-06-10
2023-06-11
2023-06-12
2023-06-13
2023-06-14
2023-06-15
2023-06-16
2023-06-17
2023-06-18
2023-06-19
2023-06-20
2023-06-21
2023-06-22
2023-06-23
2023-06-24
2023-06-25
2023-06-26
2023-06-27
2023-06-28
2023-06-29
2023-06-30
2023-07-01
2023-07-02
2023-07-03
2023-07-04
2023-07-05
2023-07-06
2023-07-07
2023-07-08
2023-07-09
2023-07-10
2023-07-11
2023-07-12
2023-07-13
2023-07-14
2023-07-15
2023-07-16
2023-07-17
2023-07-18
2023-07-19
2023-07-20
2023-07-21
2023-07-22
2023-07-23
2023-07-24
2023-07-25
2023-07-26
2023-07-27
2023-07-28
2023-07-29
2023-07-30
2023-07-31
2023-08-01
2023-08-02
2023-08-03
2023-08-04
2023-08-05
2023-08-06
2023-08-07
2023-08-08
2023-08-09
2023-08-10
2023-08-11
2023-08-12
2023-08-13
2023-08-14
2023-08-15
2023-08-16
2023-08-17
2023-08-18
2023-08-19
2023-08-20
2023-08-21
2023-08-22
2023-08-23
2023-08-24
2023-08-25
2023-08-26
2023-08-27
2023-08-28
2023-08-29
2023-08-30
2023-08-31
2023-09-01
2023-09-02
2023-09-03
2023-09-04
2023-09-05
2023-09-06
2023-09-07
2023-09-08
2023-09-09
2023-09-10
2023-09-11
2023-09-12
2023-09-13
2023-09-14
2023-09-15
2023-09-16
2023-09-17
2023-09-18
2023-09-19
2023-09-20
2023-09-21
2023-09-22
2023-09-23
2023-09-24
2023-09-25
2023-09-26
2023-09-27
2023-09-28
2023-09-29
2023-09-30
2023-10-01
2023-10-02
2023-10-03
2023-10-04
2023-10-05
2023-10-06
2023-10-07
2023-10-08
2023-10-09
2023-10-10
2023-10-11
2023-10-12
2023-10-13
2023-10-14
2023-10-15
2023-10-16
2023-10-17
2023-10-18
2023-10-19
2023-10-20
2023-10-21
2023-10-22
2023-10-23
2023-10-24
2023-10-25
2023-10-26
2023-10-27
2023-10-28
2023-10-29
2023-10-30
2023-10-31
2023-11-01
2023-11-02
2023-11-03
2023-11-04
2023-11-05
2023-11-06
2023-11-07
2023-11-08
2023-11-09
2023-11-10
2023-11-11
2023-11-12
2023-11-13
2023-11-14
2023-11-15
2023-11-16
2023-11-17
2023-11-18
2023-11-19
2023-11-20
2023-11-21
2023-11-22
2023-11-23
2023-11-24
2023-11-25
2023-11-26
2023-11-27
2023-11-28
2023-11-29
2023-11-30
2023-12-01
2023-12-02
2023-12-03
2023-12-04
2023-12-05
2023-12-06
2023-12-07
2023-12-08
2023-12-09
2023-12-10
2023-12-11
2023-12-12
2023-12-13
2023-12-14
2023-12-15
2023-12-16
2023-12-17
2023-12-18
2023-12-19
2023-12-20
2023-12-21
2023-12-22
2023-12-23
2023-12-24
2023-12-25
2023-12-26
2023-12-27
2023-12-28
2023-12-29
2023-12-30
2023-12-31
2024-01-01
2024-01-02
2024-01-03
2024-01-04
2024-01-05
2024-01-06
2024-01-07
2024-01-08
2024-01-09
2024-01-10
2024-01-11
2024-01-12
2024-01-13
2024-01-14
2024-01-15
2024-01-16
2024-01-17
2024-01-18
2024-01-19
2024-01-20
2024-01-21
2024-01-22
2024-01-23
2024-01-24
2024-01-25
2024-01-26
2024-01-27
2024-01-28
2024-01-29
2024-01-30
2024-01-31
2024-02-01
2024-02-02
2024-02-03
2024-02-04
2024-02-05
2024-02-06
2024-02-07
2024-02-08
2024-02-09
2024-02-10
2024-02-11
2024-02-12
2024-02-13
2024-02-14
2024-02-15
2024-02-16
2024-02-17
2024-02-18
2024-02-19
2024-02-20
2024-02-21
2024-02-22
2024-02-23
2024-02-24
2024-02-25
2024-02-26
2024-02-27
2024-02-28
2024-02-29
2024-03-01
2024-03-02
2024-03-03
2024-03-04
2024-03-05
2024-03-06
2024-03-07
2024-03-08
2024-03-09
2024-03-10
2024-03-11
2024-03-12
2024-03-13
2024-03-14
2024-03-15
2024-03-16
2024-03-17
2024-03-18
2024-03-19
2024-03-20
2024-03-21
2024-03-22
2024-03-23
2024-03-24
2024-03-25
2024-03-26
2024-03-27
2024-03-28
2024-03-29
2024-03-30
2024-03-31
2024-04-01
2024-04-02
2024-04-03
2024-04-04
2024-04-05
2024-04-06
2024-04-07
2024-04-08
2024-04-09
2024-04-10
2024-04-11
2024-04-12
2024-04-13
2024-04-14
2024-04-15
2024-04-16
2024-04-17
2024-04-18
2024-04-19
2024-04-20
2024-04-21
2024-04-22
2024-04-23
2024-04-24
2024-04-25
2024-04-26
2024-04-27
2024-04-28
2024-04-29
2024-04-30
2024-05-01
2024-05-02
2024-05-03
2024-05-04
2024-05-05
2024-05-06
2024-05-07
2024-05-08
2024-05-09
2024-05-10
2024-05-11
2024-05-12
2024-05-13
2024-05-14
2024-05-15
2024-05-16
2024-05-17
2024-05-18
2024-05-19
2024-05-20
2024-05-21
2024-05-22
2024-05-23
2024-05-24
2024-05-25
2024-05-26
2024-05-27
2024-05-28
2024-05-29
2024-05-30
2024-05-31
2024-06-01
2024-06-02
2024-06-03
2024-06-04
2024-06-05
2024-06-06
2024-06-07
2024-06-08
2024-06-09
2024-06-10
2024-06-11
2024-06-12
2024-06-13
2024-06-14
2024-06-15
2024-06-16
2024-06-17
2024-06-18
2024-06-19
2024-06-20
2024-06-21
2024-06-22
2024-06-23
2024-06-24
2024-06-25
2024-06-26
2024-06-27
2024-06-28
2024-06-29
2024-06-30
2024-07-01
2024-07-02
2024-07-03
2024-07-04
2024-07-05
2024-07-06
2024-07-07
2024-07-08
2024-07-09
2024-07-10
2024-07-11
2024-07-12
2024-07-13
2024-07-14
2024-07-15
2024-07-16
2024-07-17
2024-07-18
2024-07-19
2024-07-20
2024-07-21
2024-07-22
2024-07-23
2024-07-24
2024-07-25
2024-07-26
2024-07-27
2024-07-28
2024-07-29
2024-07-30
2024-07-31
2024-08-01
2024-08-02
2024-08-03
2024-08-04
2024-08-05
2024-08-06
2024-08-07
2024-08-08
2024-08-09
2024-08-10
2024-08-11
2024-08-12
2024-08-13
2024-08-14
2024-08-15
2024-08-16
2024-08-17
2024-08-18
2024-08-19
2024-08-20
2024-08-21
2024-08-22
2024-08-23
2024-08-24
2024-08-25
2024-08-26
2024-08-27
2024-08-28
2024-08-29
2024-08-30
2024-08-31
2024-09-01
2024-09-02
2024-09-03
2024-09-04
2024-09-05
2024-09-06
2024-09-07
2024-09-08
2024-09-09
2024-09-10
2024-09-11
2024-09-12
2024-09-13
2024-09-14
2024-09-15
2024-09-16
2024-09-17
2024-09-18
2024-09-19
2024-09-20
2024-09-21
2024-09-22
2024-09-23
2024-09-24
2024-09-25
2024-09-26
2024-09-27
2024-09-28
2024-09-29
2024-09-30
2024-10-01
2024-10-02
2024-10-03
2024-10-04
2024-10-05
2024-10-06
2024-10-07
2024-10-08
2024-10-09
2024-10-10
2024-10-11
2024-10-12
2024-10-13
2024-10-14
2024-10-15
2024-10-16
2024-10-17
2024-10-18
2024-10-19
2024-10-20
2024-10-21
2024-10-22
2024-10-23
2024-10-24
2024-10-25
2024-10-26
2024-10-27
2024-10-28
2024-10-29
2024-10-30
2024-10-31
2024-11-01
2024-11-02
2024-11-03
2024-11-04
2024-11-05
2024-11-06
2024-11-07
2024-11-08
2024-11-09
2024-11-10
2024-11-11
2024-11-12
2024-11-13
2024-11-14
2024-11-15
2024-11-16
2024-11-17
2024-11-18
2024-11-19
2024-11-20
2024-11-21
2024-11-22
2024-11-23
2024-11-24
2024-11-25
2024-11-26
2024-11-27
2024-11-28
2024-11-29
2024-11-30
2024-12-01
2024-12-02
2024-12-03
2024-12-04
2024-12-05
2024-12-06
2024-12-07
2024-12-08
2024-12-09
2024-12-10
2024-12-11
2024-12-12
2024-12-13
2024-12-14
2024-12-15
2024-12-16
2024-12-17
2024-12-18
2024-12-19
2024-12-20
2024-12-21
2024-12-22
2024-12-23
2024-12-24
2024-12-25
2024-12-26
2024-12-27
2024-12-28
2024-12-29
2024-12-30
2024-12-31
2025-01-01
2025-01-02
2025-01-03
2025-01-04
2025-01-05
2025-01-06
2025-01-07
2025-01-08
2025-01-09
2025-01-10
2025-01-11
2025-01-12
2025-01-13
2025-01-14
2025-01-15
2025-01-16
2025-01-17
2025-01-18
2025-01-19
2025-01-20
2025-01-21
2025-01-22
2025-01-23
2025-01-24
2025-01-25
2025-01-26
2025-01-27
2025-01-28
2025-01-29
2025-01-30
2025-01-31
2025-02-01
2025-02-02
2025-02-03
2025-02-04
2025-02-05
2025-02-06
2025-02-07
2025-02-08
2025-02-09
2025-02-10
2025-02-11
2025-02-12
2025-02-13
2025-02-14
2025-02-15
2025-02-16
2025-02-17
2025-02-18
2025-02-19
2025-02-20
2025-02-21
2025-02-22
2025-02-23
2025-02-24
2025-02-25
2025-02-26
2025-02-27
2025-02-28
2025-03-01
2025-03-02
2025-03-03
2025-03-04
2025-03-05
2025-03-06
2025-03-07
2025-03-08
2025-03-09
2025-03-10
2025-03-11
2025-03-12
2025-03-13
2025-03-14
2025-03-15
2025-03-16
2025-03-17
2025-03-18
2025-03-19
2025-03-20
2025-03-21
2025-03-22
2025-03-23
2025-03-24
2025-03-25
2025-03-26
2025-03-27
2025-03-28
2025-03-29
2025-03-30
2025-03-31
2025-04-01
2025-04-02
2025-04-03
2025-04-04
2025-04-05
2025-04-06
2025-04-07
2025-04-08
2025-04-09
2025-04-10
2025-04-11
2025-04-12
2025-04-13
2025-04-14
2025-04-15
2025-04-16
2025-04-17
2025-04-18
2025-04-19
2025-04-20
2025-04-21
2025-04-22
2025-04-23
2025-04-24
2025-04-25
2025-04-26
2025-04-27
2025-04-28
2025-04-29
2025-04-30
2025-05-01
2025-05-02
2025-05-03
2025-05-04
2025-05-05
2025-05-06
2025-05-07
2025-05-08
2025-05-09
2025-05-10
2025-05-11
2025-05-12
2025-05-13
2025-05-14
2025-05-15
2025-05-16
2025-05-17
2025-05-18
2025-05-19
2025-05-20
2025-05-21
2025-05-22
2025-05-23
2025-05-24
2025-05-25
2025-05-26
2025-05-27
2025-05-28
2025-05-29
2025-05-30
2025-05-31
2025-06-01
2025-06-02
2025-06-03
2025-06-04
2025-06-05
2025-06-06
2025-06-07
2025-06-08
2025-06-09
2025-06-10
2025-06-11
2025-06-12
2025-06-13
2025-06-14
2025-06-15
2025-06-16
2025-06-17
2025-06-18
2025-06-19
2025-06-20
2025-06-21
2025-06-22
2025-06-23
2025-06-24
2025-06-25
2025-06-26
2025-06-27
2025-06-28
2025-06-29
2025-06-30
2025-07-01
2025-07-02
2025-07-03
2025-07-04
2025-07-05
2025-07-06
2025-07-07
2025-07-08
2025-07-09
2025-07-10
2025-07-11
2025-07-12
2025-07-13
2025-07-14
2025-07-15
2025-07-16
2025-07-17
2025-07-18
2025-07-19
2025-07-20
2025-07-21
2025-07-22
2025-07-23
2025-07-24
2025-07-25
2025-07-26
2025-07-27
2025-07-28
2025-07-29
2025-07-30
2025-07-31
2025-08-01
2025-08-02
2025-08-03
2025-08-04
2025-08-05
2025-08-06
2025-08-07
2025-08-08
2025-08-09
2025-08-10
2025-08-11
2025-08-12
2025-08-13
2025-08-14
2025-08-15
2025-08-16
2025-08-17
2025-08-18
2025-08-19
2025-08-20
2025-08-21
2025-08-22
2025-08-23
2025-08-24
2025-08-25
2025-08-26
2025-08-27
2025-08-28
2025-08-29
2025-08-30
2025-08-31
2025-09-01
2025-09-02
2025-09-03
2025-09-04
2025-09-05
2025-09-06
2025-09-07
2025-09-08
2025-09-09
2025-09-10
2025-09-11
2025-09-12
2025-09-13
2025-09-14
2025-09-15
2025-09-16
2025-09-17
2025-09-18
2025-09-19
2025-09-20
2025-09-21
2025-09-22
2025-09-23
2025-09-24
2025-09-25
2025-09-26
2025-09-27
2025-09-28
2025-09-29
2025-09-30
2025-10-01
2025-10-02
2025-10-03
2025-10-04
2025-10-05
2025-10-06
2025-10-07
2025-10-08
2025-10-09
2025-10-10
2025-10-11
2025-10-12
2025-10-13
2025-10-14
2025-10-15
2025-10-16
2025-10-17
2025-10-18
2025-10-19
2025-10-20
2025-10-21
2025-10-22
2025-10-23
2025-10-24
2025-10-25
2025-10-26
2025-10-27
2025-10-28
2025-10-29
2025-10-30
2025-10-31
2025-11-01
2025-11-02
2025-11-03
2025-11-04
2025-11-05
2025-11-06
2025-11-07
2025-11-08
2025-11-09
2025-11-10
2025-11-11
2025-11-12
2025-11-13
2025-11-14
2025-11-15
2025-11-16
2025-11-17
2025-11-18
2025-11-19
2025-11-20
2025-11-21
2025-11-22
2025-11-23
2025-11-24
2025-11-25
2025-11-26
2025-11-27
2025-11-28
2025-11-29
2025-11-30
2025-12-01
2025-12-02
2025-12-03
2025-12-04
2025-12-05
2025-12-06
2025-12-07
2025-12-08
2025-12-09
2025-12-10
2025-12-11
2025-12-12
2025-12-13
2025-12-14
2025-12-15
2025-12-16
2025-12-17
2025-12-18
2025-12-19
2025-12-20
2025-12-21
2025-12-22
2025-12-23
2025-12-24
2025-12-25
2025-12-26
2025-12-27
2025-12-28
2025-12-29
2025-12-30
2025-12-31